## Project schedule
| A Team |  |  |  |  | Project start: | [7 empty] | 2025-08-04
[6 empty] | Display week: | [7 empty] | 1
| Group Members | Initials | Roles | [10 empty] | Num Tasks:
| Braydon Wooley - ST10394807 | BW | Scrum Master, Front End Dev | [11 empty] | 44
| Max van der Walt - ST10354483 | MvdW | Lead Developer | [11 empty] | 34+5
| Denzel Zimba - ST10383606 | DZ | DevOps | [11 empty] | 29+5
| Nicolas Christofides - ST10339570 | NC | Front End Dev | [11 empty] | 46+4
| Daniel Jung - ST10324495 | DJ | DevOps | [11 empty] | 33+5
[6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10
| TASK | ASSIGNED TO | START | END | time axis 2025-08-04 to 2025-11-16
 | time axis 2025-08-04 to 2025-11-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Portfolio of Evidence |  | 2025-08-04 | 2025-08-20 | 17 | 2025-08-04: SPRINT 1
| Gather system requirements from case study | MvdW | 2025-08-07 | 2025-08-10 | 4
| Write User Roles: List & describe all roles (Admin, Client, Contractor, etc.). | BW | 2025-08-10 | 2025-08-12
| Write User Stories & User Story Backlog Table | BW | 2025-08-10 | 2025-08-12
| Create use case diagrams | DZ | 2025-08-12 | 2025-08-14 | 3
| Create ERD (database design) | DZ | 2025-08-12 | 2025-08-14 | 3
| Justification for database choice (SQL or NoSQL). | MvdW | 2025-08-12 | 2025-08-14
| Create Bounded context diagramwith descriptions for each context | MvdW | 2025-08-12 | 2025-08-14
| Create class diagrams | DJ | 2025-08-12 | 2025-08-14 | 3
| Create sequence diagrams | DJ | 2025-08-12 | 2025-08-15
| Create activity diagrams | DJ | 2025-08-12 | 2025-08-15
| Create UI mockups (web + mobile) | BW+NC | 2025-08-15 | 2025-08-18 | 4
| UX Journey Map: Full journey map per role. | BW+NC | 2025-08-15 | 2025-08-18
| Create Navigation Flow Diagrams: Role-specific navigation paths. | BW+NC | 2025-08-15 | 2025-08-18
Write | Write Non-Functional Requirements | DZ | 2025-08-15 | 2025-08-18
| Set up GitHub repository | DZ | 2025-08-10 | 2025-08-12 | 3
| Create Document to explain Deployment process and requirements | MvdW | 2025-08-10 | 2025-08-18
| Create Document to explain selections of tech stack and tools | MvdW | 2025-08-10 | 2025-08-18 | 9
| Web & Mobile App Development (shared with REST API) |  |  |  |  | 2025-08-18: SPRINT 2; 2025-08-29: SPRINT 3
Back-End (ASP.NET Core, shared by web & mobile) | bar: 2025-08-18 to 2025-09-13
| Set up ASP.NET solution structure | MvdW | 2025-08-18 | 2025-08-22 | 5
| Configure authentication & role management | MvdW | 2025-08-18 | 2025-08-22
| Create database models (users, projects, requests, documents, invoices) | MvdW | 2025-08-20 | 2025-08-25
M | Implement CRUD controllers for all entities | MvdW+NC | 2025-08-20 | 2025-08-25
| Build maintenance workflow logic | MvdW+NC | 2025-08-20 | 2025-08-25
| Build quotation & invoice logic | MvdW+NC | 2025-08-21 | 2025-08-26
| Plan messaging system API endpoints | MvdW+NC | 2025-08-21 | 2025-08-26
| Plan document upload/download endpoints | MvdW+NC | 2025-08-21 | 2025-08-26
| Create reporting data endpoints | MvdW+NC | 2025-08-22 | 2025-08-28
| Secure API (JWT, SSL, CORS policies) | MvdW | 2025-08-22 | 2025-08-28
Web Front-End (ASP.NET Razor Pages/Blazor)
| Create Admin dashboard UI (View, Edit, Delete) | NC+BW | 2025-08-28 | 2025-09-02
| Create Project Manager dashboard UI (View, Edit, Create, Delete) | NC+BW | 2025-08-28 | 2025-09-02 | 6
| Create Contractor dashboard UI (View, Edit, Delete) | NC+BW | 2025-08-28 | 2025-09-02
| Create Client dashboard UI (View, Edit, Create, Delete) | NC+BW | 2025-08-28 | 2025-09-02
| Build login & registration pages | NC+BW | 2025-09-02 | 2025-09-07
| Implement role-based navigation | NC+BW | 2025-09-02 | 2025-09-07
| Develop forms for project creation | NC+BW | 2025-09-02 | 2025-09-07
| Develop forms for maintenance request submission | NC+BW | 2025-09-02 | 2025-09-07
| Build messaging system interface | NC+BW | 2025-09-07 | 2025-09-12
| Create document upload & view interface | NC+BW | 2025-09-07 | 2025-09-12
| Develop Quotation and Invoice UI | NC+BW | 2025-09-07 | 2025-09-12
| Build reporting & dashboard UI (Visual chart, Gantt, Pie, Bar, and Line charts) | NC+BW | 2025-09-07 | 2025-09-12
Mobile Front-End (Xamarin/MAUI or React Native)
| Create Admin dashboard UI (View, Edit, Delete) | NC+BW | 2025-08-28 | 2025-09-02 | 6
| Create Project Manager dashboard UI (View, Edit, Create, Delete) | NC+BW | 2025-08-28 | 2025-09-02
| Create Contractor dashboard UI (View, Edit, Delete) | NC+BW | 2025-08-28 | 2025-09-02
| Create Client dashboard UI (View, Edit, Create, Delete) | NC+BW | 2025-08-28 | 2025-09-02
| Build login & registration pages | NC+BW | 2025-09-02 | 2025-09-07
| Implement role-based navigation | NC+BW | 2025-09-02 | 2025-09-07
| Develop forms for project creation | NC+BW | 2025-09-02 | 2025-09-07
| Develop forms for maintenance request submission | NC+BW | 2025-09-02 | 2025-09-07
| Build messaging system interface | NC+BW | 2025-09-07 | 2025-09-12
| Create document upload & view interface | NC+BW | 2025-09-07 | 2025-09-12
| Develop Quotation and Invoice UI | NC+BW | 2025-09-07 | 2025-09-12
| Build reporting & dashboard UI (Visual chart, Gantt, Pie, Bar, and Line charts) | NC+BW | 2025-09-07 | 2025-09-12
| Security & Audit Logs |  |  |  |  | 2025-08-18: SPRINT 2
| Write Test Plan: Written plan covering unit testing, integration testing, and UAT. | DJ+DZ | 2025-08-18 | 2025-08-22 | 5
| Write Sample Test Cases | DJ+DZ | 2025-08-18 | 2025-08-22
Write | Write Bug Tracking Process Decide tool (e.g., GitHub) + describe workflow | DJ+DZ | 2025-08-18 | 2025-08-22
| Integration of SonarQube in CI/CD pipeline for static code analysis. | DJ+DZ | 2025-08-18 | 2025-08-22
| Implement secure authentication (hashing, SSL config) | DJ+DZ | 2025-08-20 | 2025-08-23 | 4
| Implement failed login attempt tracking | DJ+DZ | 2025-08-20 | 2025-08-23
| Add role-based access control middleware | DJ+DZ | 2025-08-20 | 2025-08-23
| Create audit logs for document downloads | DJ+DZ | 2025-08-23 | 2025-08-26
| Create audit logs for project/maintenance updates | DJ+DZ | 2025-08-23 | 2025-08-26
| Testing App Security (Snyk) | DJ+DZ | 2025-09-30 | 2025-11-01 | bar: 2025-09-30 to 2025-11-01
| DevOps Practices: Ci/CD Documentation (Explain process) | DJ+DZ | 2025-10-01 | 2025-10-08
| DevOps Practices: Cloud Deployment Workflow (Step-by-step plan for deployment) | DJ+DZ | 2025-10-01 | 2025-10-08
| REST API |  |  |  |  | 2025-08-28: SPRINT 4
| Plan API endpoint structure | MvdW | 2025-08-28 | 2025-09-02 | 6
| Implement authentication endpoints | MvdW+DJ | 2025-09-02 | 2025-09-06
| Create project management endpoints | MvdW+DJ | 2025-09-02 | 2025-09-06
| Create maintenance request endpoints | MvdW+DJ | 2025-09-06 | 2025-09-10
| Create contractor assignment endpoints | MvdW+DJ | 2025-09-06 | 2025-09-10
| Create messaging endpoints | MvdW+DJ | 2025-09-10 | 2025-09-14
| Create document upload/download endpoints | MvdW+DJ | 2025-09-10 | 2025-09-14
| Implement quotation & invoice endpoints | MvdW+DJ | 2025-09-14 | 2025-09-18
| Test all endpoints with Postman | MvdW+DJ | 2025-09-14 | 2025-09-18
| Quotation & Invoice System |  |  |  |  | 2025-09-14: SPRINT 5
| Create quotation creation form | DZ+NC | 2025-09-14 | 2025-09-18 | 5
| Implement plan upload function (PDF/DWG) | DZ+NC | 2025-09-18 | 2025-09-25
| Implement plan parsing (basic extraction without complex AI first) | DZ+NC | 2025-09-18 | 2025-09-25
| Generate cost breakdown structure | DZ+NC | 2025-09-18 | 2025-09-25
| Add quote approval/rejection workflow | DZ+NC | 2025-09-25 | 2025-10-02
| Convert approved quotes to invoices | DZ+NC | 2025-09-25 | 2025-10-02
| Integrate payment status tracking | DZ+NC | 2025-09-25 | 2025-10-02
| AI-Powered Assistant |  |  |  |  | 2025-09-14: SPRINT 5
| Research AI options for blueprint analysis | MvdW + BW | 2025-09-14 | 2025-09-18 | 5
| Prepare sample blueprint files for testing | BW | 2025-09-18 | 2025-09-25
| Implement basic blueprint file parsing | MvdW + BW | 2025-09-18 | 2025-09-25
| Create mock AI cost estimation (manual logic first) | DJ | 2025-09-18 | 2025-09-25
| Explore API-based AI services (e.g., Azure Cognitive Services) | DJ | 2025-09-25 | 2025-10-02
| Integrate AI cost estimation into quotation module | MvdW +DJ | 2025-09-25 | 2025-10-02
| Implement basic project delay prediction logic | MvdW +DJ | 2025-09-25 | 2025-10-02
| Test AI outputs and refine | BW | 2025-10-02 | 2025-10-10
| Bonus - Voice Feedback |  |  |  |  | 2025-10-02: SPRINT 6
| Research voice recording library for web/mobile | MvdW + DZ + DJ | 2025-10-02 | 2025-10-10 | 9
| Design UI for Voice Recording Pages | MvdW + DZ + DJ | 2025-10-10 | 2025-10-16
| Implement contractor voice memo upload | MvdW + DZ + DJ | 2025-10-10 | 2025-10-16
| Store and retrieve voice memos in database | MvdW + DZ + DJ | 2025-10-10 | 2025-10-16
| UX Design |  |  |  |  | 2025-10-16: SPRINT 7
| Finalize responsive design for web app | NC+BW | 2025-10-16 | 2025-10-18 | 3
| Finalize responsive design for mobile app | NC+BW | 2025-10-18 | 2025-10-20 | 3
| Test UI on multiple devices | NC+BW | 2025-10-20 | 2025-10-23
| Adjust based on feedback | NC+BW | 2025-10-23 | 2025-10-30 | 8
| Deployment |  |  |  |  | 2025-10-16: SPRINT 7
| Prepare Production Environment: Create Firebase project. | MvdW | 2025-10-23 | 2025-10-25 | 3
| Configure Web Server: Use Firebase Hosting for the web front end. | MvdW | 2025-10-25 | 2025-10-28
| Configure Database: Create Firestore in production mode. Add required indexes. | MvdW | 2025-10-25 | 2025-10-28
| Build and Publish Web App: Build the front end for production | NC+DZ | 2025-10-25 | 2025-10-28
| Deploy REST API: Containerize the ASP.NET Core API. Deploy to Cloud Run (managed) | NC+DZ | 2025-10-25 | 2025-10-28
| Mobile App Packaging: Build signed Android AAB and iOS IPA (if applicable). | NC+DJ | 2025-10-25 | 2025-10-28 | 4
| Upload Mobile App to Store/Distribution: Use Firebase App Distribution for testers. | NC+DJ | 2025-10-25 | 2025-10-28
| CI/CD Integration: GitHub Actions | DJ + DZ | 2025-10-25 | 2025-10-28
| Cloud Storage Setup: Configure Firebase Storage buckets and security rules. | DJ + DZ | 2025-10-25 | 2025-10-28
| Final Security Checks: Run Snyk on API container and repo. Run SonarQube. | DJ + DZ | 2025-10-28 | 2025-10-30
| Smoke Testing: Hit Cloud Run API with Postman. | MvdW | 2025-10-30 | 2025-11-02 | 4
| Post-Deployment Monitoring: Enable Firebase Crashlytics & Performance Monitoring. | MvdW | 2025-10-30 | 2025-11-02 | 4
| Presentation & System Demo |  |  |  |  | 2025-10-30: SPRINT 8
| Prepare system presentation slides | BW | 2025-10-30 | 2025-11-02 | 4
| Record demo video of web app | BW | 2025-10-30 | 2025-11-02
| Record demo video of mobile app | BW | 2025-10-30 | 2025-11-02
| Combine videos for final presentation | BW | 2025-10-30 | 2025-11-02
| Practice presentation delivery | BW | 2025-10-30 | 2025-11-02
Peer Collaboration & Evaluation
| Maintain commit history in GitHub | ALL | 2025-08-10 | 2025-11-02 | 85
| Keep feature branch documentation | ALL | 2025-08-10 | 2025-11-02 | 85
| Submit individual contribution logs | ALL | 2025-10-31 | 2025-11-02 | 3

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.